## Procurement Tracker
PO Number | Material Code | Material Description | Category | Vendor | Manufacturer | Quantity | Unit | Unit Price | Total Price | Currency | PO Date | Required Date | Promised Delivery | Actual Delivery | Delivery Status | Lead Time (Days) | Delay (Days) | Warehouse | Building | Area | WBS | Activity ID | Responsible Engineer | Critical Item | Risk Level | Remarks
PO-2024-0041 | UPS-500KVA | 500kVA UPS | Electrical | Schneider Electric | Schneider | 2 | Nos | 4500000 | 9000000 | INR | 2026-07-01 | 2026-07-20 | 2026-07-18 | 2026-07-19 | Delivered | 18 | 0 | WH-A | B1 | Electrical Room | WBS-EL-01 | ELE-145 | Rahul Sharma | Yes | Low | Installed
PO-2024-0042 | DG-2250 | 2250kVA Diesel Generator | Electrical | Cummins | Cummins | 4 | Nos | 7800000 | 31200000 | INR | 2026-07-02 | 2026-07-30 | 2026-08-05 |  | Delayed | 34 | 6 | WH-B | B1 | Generator Yard | WBS-EL-02 | ELE-160 | Ankit Verma | Yes | High | Vendor delay
PO-2024-0043 | CRAC-60T | CRAC Unit | HVAC | Vertiv | Vertiv | 10 | Nos | 1250000 | 12500000 | INR | 2026-07-05 | 2026-08-01 | 2026-08-01 |  | In Transit | 27 | 0 | WH-C | B2 | Data Hall | WBS-HV-01 | HVAC-120 | Priya Singh | Yes | Medium | Shipment in transit
PO-2024-0044 | PDU-160 | 160A PDU | Electrical | Eaton | Eaton | 25 | Nos | 85000 | 2125000 | INR | 2026-07-06 | 2026-08-10 | 2026-08-09 |  | Ordered | 30 | 0 | WH-A | B2 | Data Hall | WBS-EL-03 | ELE-210 | Rohit Gupta | No | Low | Awaiting dispatch
PO-2024-0045 | CAB-3C240 | 3C x 240 sqmm Cable | Electrical | Polycab | Polycab | 5000 | m | 1200 | 6000000 | INR | 2026-07-03 | 2026-07-25 | 2026-07-27 |  | Delayed | 24 | 2 | WH-D | B1 | Cable Yard | WBS-EL-04 | ELE-175 | Neha Jain | Yes | Medium | Transport delay